## Sheet1
Group: | PG04 | Software Engineering & Project Semester 2 2016
Stuent Id | Name | Week 3 |  | Week 4 |  | Week 5 |  | Week 6 |  | Week 7 |  | Week 8 |  | Week 9 |  | Week 10 |  | Week 11 |  | Week 12
|  | Activity | Outcome | Activity | Outcome | Activity | Outcome | Activity | Outcome | Activity | Outcome | Activity | Outcome | Activity | Outcome | Activity | Outcome | Activity | Outcome | Activity | Outcome
1680974 | Tao Zhang | Prepare for client meetings | generate questions for meeting
|  | Fimiliar with leJos | example code for accessing sensor and motor
1680895 | Zeqi Fu | Read the requirement document | Find out some questions for meeting
|  | Help groupmates working on srs | Help with srs draft
|  | Take part in group reauglar meeting | Discuss questions with teammates
|  | Read LeJOS java API, Do some simple demo on robot | Demo code on robot
1679380 | Liang Yuan | familiar with document, configure lejos environment，come up with requirement with members | got ideas about sensors
1162562 | Yann Frizenschaf | SRS draft/requirements elicitation | SRS draft ready for client meeting
|  | Investigating/installing tools | Development and Git tools ready
|  | Poster text proofreading | Poster text ready for submission
1683229 | Lili Wu | requirements elicitation | in progress
|  | learn latex | done
|  | poster text | done
|  | configure lejos operation envioronment | done
1660360 | Navdeep Singh | Learn Latex | able to Write Latex Document
|  | Go through the Project Requirement | come up with questions to ask the Client
|  | Work on Poster | Poster Submitted
|  | Information gathering by attending internal group meeting | help group in dividing the work load
|  | week 3 Client Meeting minutes | what client want and make clear understanding of the Project
1682781 | Yi Lin | reading the document, summary the client requirements | week3 agenda client requirement summarize github new file build
|  | learning the latex | write agenda
|  | fimilar the Github | creat new file
|  | testing the example code online (making the robot move) | robot move
|  | writing the agenda of week3 | week3 agenda