## Sheet1
Group: | PG04 | Software Engineering & Project Semester 2 2016
Stuent Id | Name | Week 3 |  | Week 4 |  | Week 5 |  | Week 6 |  | Week 7 |  | Week 8 |  | Week 9 |  | Week 10 |  | Week 11 |  | Week 12
|  | Activity | Outcome | Activity | Outcome | Activity | Outcome | Activity | Outcome | Activity | Outcome | Activity | Outcome | Activity | Outcome | Activity | Outcome | Activity | Outcome | Activity | Outcome
1680974 | Tao Zhang | Prepare for client meetings | generate questions for meeting
|  | Fimiliar with leJos | example code for accessing sensor and motor
1680895 | Zeqi Fu | Read the requirement document | Find out some questions for meeting | Be a chair in week4 client meeting | Chair | Helping with spmp document
|  | Help groupmates working on srs | Help with srs draft | Agenda ready for meeting | Woking on agenda and ready for it | working on lejos basic fuction | progress
|  | Take part in group reauglar meeting | Discuss questions with teammates
|  | Read LeJOS java API, Do some simple demo on robot | Demo code on robot
1679380 | Liang Yuan | familiar with document | got ideas about sensors | work on ultrasonic sensor | get distance from ultra-sensor | Week 5 meeting minutes | done
|  | configure lejos environment | environment ready | familiar with LeJos | in Progress | ultrasonic sensor program | done
|  | come up with requirement with members | get requirement
1162562 | Yann Frizenschaf | SRS draft/requirements elicitation | SRS draft ready for client meeting | Group meeting | Feature teams defined, project manager appointed | SRS Draft updates | SRS Draft completed
|  | Investigating/installing tools | Development and Git tools ready | Software interface definitions | Draft UML created, major class skeletons and interfaces defined (initial ideas only) | PM - Creating tickets | Tracking system updated
|  | Poster text proofreading | Poster text ready for submission | Week 4 client meeting minutes | Minutes document generated | GUI updates | Initial JavaFX gui created
|  |  |  | PM: Defining tasks for group members | Sprint 1 tasks defined | Merging prototype code into main project | Monolithic code better organised
[6 empty] | Preparation for demo | Demo code ready
1683229 | Lili Wu | requirements elicitation | in progress | SRS update | done | SPMP update | in progress
|  | learn latex | done | Find out potential requirements for next week's meeting | done
|  | poster text | done | study java | in progress
|  | configure lejos operation envioronment | done | colour sensor research | in progress
1660360 | Navdeep Singh | Learn Latex | able to Write Latex Document | Learn Lejos | in Progress | getting Familiar with Lejos and learn more java GUI, etc | On Going
|  | Go through the Project Requirement | come up with questions to ask the Client | Instal required environment | installed Eclipse | Worked on SPMP | Completed the initial Draft for SPMP
|  | Work on Poster | Poster Submitted | Group Meeting | got Assigned some internal Tasks
|  | Information gathering by attending internal group meeting | help group in dividing the work load | get Familiar with git | able to do commits,pull,push and other basic commands from terminal
|  | week 3 Client Meeting minutes | what client want and make clear understanding of the Project
1682781 | Yi Lin | reading the document, summary the client requirements | week3 agenda client requirement summarize github new file build | reading the documents continue | summary the document
|  | learning the latex | write agenda | study java | some study materials | SRS Draft improvement | improve the GUI part in SRS
|  | fimilar the Github | creat new file | study GUI of java | GUI design | SPMP-Risk Management | finish risk management
|  | testing the example code online (making the robot move) | robot move
|  | writing the agenda of week3 | week3 agenda